## Migration Plan
| o |  | Legend： | Planned | Finished | Ongoing | Delayed | Blocked
Workstream | Overall Progress | 1% |  | Current Stage：Preparation | [5 empty] | Schedule |  |  | M0 |  |  |  | M1 |  |  |  | M2 |  |  |  | M3 |  |  |  | M4 |  |  |  | M5 |  |  |  | M6 |  |  |  | M7 |  |  |  | M8 |  |  |  | M9 |  |  |  | M10 |  |  |  | M11 |  |  |  | M12
| Stage | Task |  | Desc | progress | Status | Customer | Tencent | Tools | Start Time | Finish Time | May 2024 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Workload | Stage1： Prepare | Information Collection | Cloud Product Information Collection | Billing information collection |  | ongoing |  |  | SKU usage bills("actual cost" column deleted) | bar: May 2024 to M0 W4
|  |  | Product & Resource Infomation Collection | Resource information collection |  | not started |  |  | SKU usage bills("actual cost" column deleted) | bar: May 2024 to M0 W4
|  |  |  | Cloud products / components information collection |  | not started |  |  | Read Only Account | bar: May 2024 to M0 W4
|  |  |  | Performance / Monitorning metrics collection |  | not started |  |  | Read Only Account | bar: M0 W1 to M0 W4
|  | Sign Contract |  | Sign the contract, Migration kickoff |  | not started | bar: M0 W1 to M0 W4
|  | Tencent Account |  | Tencent Cloud account preparation |  | not started | bar: M0 W1 to M0 W4
|  | Training on Tencent Cloud Products | Tencent Product & Service | Compute (CVM) |  | not started | bar: M1 W1 to M2 W4
|  |  |  | Storage (CBS, COS, CFS, etc.) |  | not started | bar: M1 W1 to M2 W4
|  |  |  | Network (VPC, CLB, CCN, VPN, etc) |  | not started | bar: M1 W1 to M2 W4
|  |  |  | Big Data (Wedata, EMR, DLC, etc) |  | not started | bar: M1 W1 to M2 W4
|  |  |  | Containers (TKE, TCR, etc) |  | not started | bar: M1 W1 to M2 W4
|  |  |  | Middleware (KMS, Database, MQ, TSF, etc) |  | not started | bar: M1 W1 to M2 W4
|  |  |  | Security (CFW, EdgeOne, ) |  | not started | bar: M1 W1 to M2 W4
|  |  |  | Terraform (Tencent Cloud Provider) |  | not started | bar: M1 W1 to M2 W4
| Stage2： Design | Business Architecture Research | Migration Solution Design | Business module research |  | not started | bar: M0 W1 to M0 W4
|  |  |  | Business dependency mapping |  | not started | bar: M0 W1 to M0 W4
|  |  |  | Resource usage analysis for each business module |  | not started | bar: M0 W1 to M0 W4
|  |  |  | Business SLA collection |  | not started | bar: M0 W1 to M0 W4
|  | Network Solution Design | Network | Network topology research |  | not started | bar: M0 W1 to M0 W4
|  |  |  | Network ACL research |  | not started | bar: M0 W1 to M0 W4
|  |  |  | Tencent Cloud network design (VPC / VPC Peer, etc.) |  | not started | bar: M0 W1 to M0 W4
|  |  |  | Designing the dedicated line solution during migration |  | not started | bar: M0 W3 to M0 W4
|  |  |  | Dedicated line construction |  | not started | bar: M1 W1 to M2 W4
|  | Product Feature Proof of Concept (PoC) Testing & Validation | Tencent Product & Service | Compute (CVM) |  | not started | bar: M1 W1 to M2 W4
|  |  |  | Storage (CBS, COS, CFS, etc.) |  | not started | bar: M1 W1 to M2 W4
|  |  |  | Network (VPC, CLB, CCN, VPN, etc) |  | not started | bar: M1 W1 to M2 W4
|  |  |  | Containers (TKE, TCR, etc) |  | not started | bar: M1 W1 to M2 W4
|  |  |  | Middleware (Database, MessageQueue, etc) |  | not started | bar: M1 W1 to M2 W4
|  |  |  | Terraform (Tencent Cloud Provider) |  | not started | bar: M1 W1 to M2 W4
|  |  |  | Reference Micro-service Example |  | not started | bar: M1 W1 to M2 W4
|  | Service Migration Plan & Solution Design | For each APPs & Platform & Engineering Platform | Overall Migration Plan |  | not started | bar: M0 W1 to M0 W4
|  |  |  | Detail Code adaptation and compatibility solution & plan |  | not started | bar: M1 W1 to M3 W4
|  |  |  | Detail Detail Deployment solution & plan |  | not started | bar: M1 W1 to M3 W4
|  |  |  | Detail Data migration solution & plan |  | not started | bar: M1 W1 to M3 W4
|  |  |  | Detail Service testing solution & plan |  | not started | bar: M1 W1 to M3 W4
|  |  |  | Detail Drill solution & plan |  | not started | bar: M1 W1 to M3 W4
|  |  |  | Detail Rollback solution & plan |  | not started | bar: M1 W1 to M3 W4
|  |  |  | Detail Cut-over solution & plan |  | not started | bar: M1 W1 to M3 W4
| Stage3： Implementation | DevOps platform | Terraform platform integration | Integrate with Tencent Cloud Terraform |  | not started | bar: M1 W1 to M3 W4
|  |  | CI/CD/Internal tools/etc. | adaptation with Tencent Cloud |  | not started | bar: M2 W1 to M3 W4
|  | Infra Deployment | IAM Deployment | Account/privileage/tag/lable deployment |  | not started | bar: M3 W1 to M3 W4
|  |  | Monitoring& alert deployment | Deploy monitoring and alert system |  | not started | bar: M3 W1 to M3 W4
|  |  | billing system Integration | Billing system integration with tencent cloud |  | not started | bar: M3 W1 to M3 W4
|  |  | Securty deployment | VM/WAF/security deployment |  | not started | bar: M3 W1 to M3 W4
|  |  | Audit sytem deployment | Auidt log |  | not started | bar: M3 W1 to M3 W4
|  |  | VPC/Subnet deployment | VPC/Subnet deployment |  | not started | bar: M3 W1 to M3 W4
|  | Service Deployment & Migration for each Apps & Platforms | Tencent product & service adapataion | Object storage SDK |  | not started | bar: M2 W1 to M3 W4
|  |  |  | APIs & Tencent product adapation |  | not started | bar: M2 W1 to M3 W4
|  |  | Object storage migration | migrate object storage to COS |  | not started | bar: M4 W1 to M6 W4
|  |  | File storage migration | Migrate file storage to CFS |  | not started | bar: M4 W1 to M6 W4
|  |  | service deployment | Deploy service on Tencent cloud |  | not started | bar: M4 W1 to M6 W4
|  |  | database migration | Migrate database（redis/pg） |  | not started | bar: M4 W1 to M6 W4
|  |  | business function test | Function test |  | not started | bar: M4 W1 to M6 W4
|  |  | business load test | Load test |  | not started | bar: M4 W1 to M6 W4
|  |  | service HA test | HA test on tencent |  | not started | bar: M4 W1 to M6 W4
|  |  | cutover tool develpment | Prepare cutover tool and scripts |  | not started | bar: M4 W1 to M6 W4
|  |  | prepare cutover runbook | Cutover runbook |  | not started | bar: M4 W1 to M6 W4
|  |  | prepare rollback runbook | Rollback runbook |  | not started | bar: M4 W1 to M6 W4
|  |  | first cutover dry-run | cutover dry-run and runbook elaborate |  | not started | bar: M4 W1 to M6 W4
|  |  | second cutover dry-run | cutover dry-runr and runbook elaborate |  | not started | bar: M4 W1 to M6 W4
|  |  | third cutover dry-run | cutover dry-run and runbook elaborate |  | not started | bar: M4 W1 to M6 W4
|  |  | switch CVM to new AZ | switch cvm from 2AZ model to 3AZ model after 3rd AZ in operation |  | not started | bar: M6 W1 to M6 W4
| Stage4： Cutover | First Batch Cutover | non-production enviroment | dev environment uat environment |  | not started | bar: M7 W1 to M7 W4
|  | Second Batch Cutover (Platform & services which is independent ) |  |  |  | not started | bar: M8 W1 to M8 W4
|  | Third Batch Cutover (Platform & services which is independent ) |  |  |  | not started | bar: M8 W1 to M8 W4
|  | … |  |  |  | not started | bar: M8 W1 to M8 W4
| Stage 5：summary & feature improvement | Observation |  | Observe service stability |  | not started | bar: M10 W1 to M11 W4
|  | Optimaztion |  | performance optimazation |  | not started | bar: M10 W1 to M11 W4

## Invest-Outline
Tencent Cloud Application Cloud Migration Survey Outline
We will have surveys and interviews with the application owner, architecture, core engineer, etc., in order to find out the basic situation of the application, infrastructure, development and deployment details, the current running status, and provide sufficient knowledge for the migration plan. The research is mainly conducted through interviews, document reading, data collection from the other cloud vendors and Q&A.
Basic Information
Name
Business Domain
| Business Description |  |  |  |  | Sample of Deployment Architecture Diagram
| Application Owner | Contact Information (Email / Slack / IM…) |  |  |  | This generally refers to the deployment architecture of the application, which includes the distribution of resources in the cloud and their interrelationships, mainly at the infrastructure level.
| Architecture / Tech Lead | Contact Information (Email / Slack / IM…)
| Developer / Vendor | Contact Information (Email / Slack / IM…) |  | Responsible for the code changes
| Q&A / Vendor | Contact Information (Email / Slack / IM…) |  | Responsible for the application function and performance verification
| OPS / Vendor | Contact Information (Email / Slack / IM…) |  | Responsible for the deployment and infrastructure changes
Infrastructure Survery
| ENV | how many running environments of this application, like: dev / uat / canary / prod-tl or prod-sh
| ENV | we will collect the infra resources by enviroments.
Computing Resources
|  | VM | Lists the virtual machines (AWS EC2, Alibaba ECS and the other VMs) in the current environment, with type size, storage, region and azs.
|  | Container | If this app is deployed in container env, like k8s or docker-compose, list the container resources of all pods.
|  | Function Computing | If this app is running in AWS lambda or the other FC runtime, list the function instances.
|  | Others | For the other computing resources, list the details, for example bare metal servers or GPU clusters.
Persistence
|  | RDBMS | List the instances of Relational Databases, like RDS MySQL, PostgreSQL and rest.
|  | NoSQL | The NoSQL databases, like MongoDB, DynamoDB and others.
|  | NewSQL | NewSQL databases, like TiDB, CockroachDB, TDSQL-C and others.
|  | Object Storage | S3, OSS, MinIO and the other S3 like object storage.
|  | File Storage | File system like NAS, Cloud FileSystem and rests.
|  | Others | The on-prem databases like Oracle, DB2 and the other important systems around persistence instances, like AWS Athena
BigData
|  | ADB | Analytical databases, BigQuery, SonwFlake, Redshift and rest. |  |  | Sample of Business Architecture Diagram
|  | Warehouse & Lake | Doris, Clickhouse, Teradata, EMR, MaxCompute and rest. |  |  | A business architecture diagram typically represents the business logic, particularly the dependencies of the application, upstream and downstream systems, etc.
|  | Data Development | The development tool or framework for data processing of this application
|  | Others | Other important resourecs in bigdata domain of this application.
Middleware
|  | MessageQueue | Message queue like Rocket MQ, AMQ and SQS.
|  | Pub/Sub | System for Pub/Sub of this application, like Kafka, AWS Kinesis and rest.
|  | Others | Any systems for asynchronous invocation and decoupling.
Network
|  | VPC and Subnets | Like the network structure of this app, including VPC, Subnet and Network ACL if required.
|  | LB and Gateway | Collect the Load Balancer / Gateway / Ingress.
|  | Domain Names | The public / private domain names of this app, the DNS service provider.
|  | CDN | The CDN usage of the application, accelerated domain names and objects, etc.
|  | Others | Other important network components, such as VPNS, private lines or SDWAN, etc.
Security
|  | WAF | Collect the WAF usage, including access mode, bandwidth, protection mode, access mode, etc.
|  | Firewall | Cloud firewall or the on prem firewall (PaloAlto) for this application.
|  | Security Groups and NACL | List the SG of this applications, and network access control list if exists.
|  | Bastion | Sort out the usage of jump servers of bastion.
|  | Data Security | The data security requirement, and KMS for example.
|  | SSL certificates | The certs of this app.
The other security resources (HSM, security devices etc.)
Monitoring
|  | Healthcheck | How the health of the application is checked, and whether there is a dashboard for monitoring.
|  | APM | Details of the application performance monitoring, how to integrate and monitoring.
|  | Logging | Log system.
|  | Mertics & Alerting | This application's monitoring metrics and alarm methods.
Application Architecture Survey
Tech Stack
Programming Language
Frameworks and Libraries
Frontend Technologies
Backend Technologies
DevOps Tools
External APIs / SDK
Application Dependencies
|  | Application Name | Endpoint | Interactive Method (Sync/Async 1:1/1:N) | Business relationship statement
|  | Application Name | Endpoint | Interactive Method (Sync/Async 1:1/1:N) | Business relationship statement
|  | Application Name | Endpoint | Interactive Method (Sync/Async 1:1/1:N) | Business relationship statement
...
Codebase
SourceCode Repo
IaC Code and others
DevOps
CI/CD Pipeline
IaC Implementation
Configuration
Performance Metrics
| Q&A Methods |  | Investigate the application's testing methods, unit testing, functional testing, and performance testing.
RTO/RPO
|  | Maximum Acceptable Downtime | Collect these cirtical metrics in disaster recovery and business continuty planning will help us set clear about the recovery time and data loss, for the potential distruptions.
Recovery Time Objective (RTO)
Recovery Point Objective (RPO)
Security & Compliance
| Security Principle Learning |  | Understand existing security policies and compliance requirements. The entire migration process must comply with the customer's security and compliance requirements.
| Data Security Requirement |  | Learn the organization's data security principle and requirements of this app, such as mandatory factors such as GDPR, PII.
| Migration Processing Security |  | Evaluate security risks during migration and formulate corresponding security policies and measures to ensure migration security.
Technical Team Survey
| Technical Team Session |  | Understand the capabilities and experience of the existing technical team. Assess the level of support from the team during the cloud migration process.
| Tecent Cloud Training |  | Identify the potential involvement and training requirements from Tencent's side during the migration process.
Migration Plan: Landing Zone, Cloud Architecture (Resource and Costing), Migration Plan Details
| Landing Zone Design |  | Based on Tencent Landing Zone best practice, Design a Landing Zone for the application's cloud migration, including networking, identity, security, monitoring, logging, etc.
| Resource Planning and Costing |  | Analyze the cost components during the migration process, including cloud, software, migration manpower, and time costs, and develop a reasonable cost budget and optimization strategy.
| Previous Migration Group Description |  | Describe the migration group of this application: Lift and Shift, Partial Migration, Re-Design & Migrate
| Previous Migration Plan |  | Details of the previous migration plan and questions.
Previous Migration Compatibility
Previous Priority
Open Questions
1. 4+1 architecture diagram, we should have deployment view and logic view for this app.
2. Challenges of this application in the current business scenario
3. Do we have document of 1 pager to contain the details of this app?
4. For this app, why the previous migration plan wasn't executed?

## Process
No. | Process | Description | Completion Criteria
1 | Project preparation | Party A proposes service requirements to Party B, and the Parties identify the key personnel involved as well as the requirements, necessary preparations, processes, arrangements, etc. | Party B sets up an implementation team, and confirms that the onsite conditions for implementation have been satisfied.
2 | Research and assessment | Party B collects information on the application architecture, deployment architecture, technology stack, software and hardware dependencies, resource utilization, and other aspects of the cloud-based system. Party A assesses the risks and strategies for migrating the application to the cloud. | Party B submits the "Customer Business System Information Research Report" and the "Customer Business System Cloud Migration Assessment Report". Both parties have reached an agreement on the contents of the reports.
3 | Development of cloud migration solutions | Party B will develop a detailed plan for migrating the system to the cloud, including strategies, contingency plans, resource planning, and progress tracking. | Both parties confirm the "Customer Business System Cloud Migration Technical Plan" and the "Customer Business System Cloud Migration Plan" and reach a consensus on the implementation details.
4 | Environment preparation | Party B assists Party A to prepare cloud product resources required to migrate the application to the cloud, including CVM, cloud database and cloud storage.
5 | Migration testing | Party A performs migration testing for storage, databases, middleware, and applications, as well as cutover testing in the development environment.
6 | Migration | Party A performs the migration of databases, middleware, and applications in the production environment.
7 | Performance testing | Party A's application R&D team conducts functional and performance testing on the application.
8 | System cutover | Once the testing is successfully completed, the traffic will be redirected to the new system. | "Acceptance Report on Customer Business Systems Migration"
9 | Stabilization | 5 days stable operation post-cutover. Monitor system availability, business metrics, HA. TSA inspection for optimization. | No cloud-caused incidents (15 calendar days)
10 | Service acceptance | After 5 days of stable operation following the system cutover,Party B prepares the service acceptance materials and documentation. | Party B submits the " Acceptance Report on Customer Business Systems Migration", and Party A signs the report to confirm the acceptance.

## RACI
Stage | # | Tasks | Client | Tencent | R | Responsible | The person or team who actually does the work to complete the task. They are the "doer" and are responsible for getting the job done.
Prepare | 1 | Migration scope definition | R | S | A | Accountable | The person ultimately answerable for the correct and thorough completion of the task. This person delegates the work and is the one who signs off on the final deliverable. Golden Rule
| 2 | Provide resource inspection tools | S | R | C | Consulted | Those whose opinions are sought. They provide subject-matter expertise or advice and engage in two-way communication to shape the work.
| 3 | Resource inspection(OR Tencent can do it with RO account provided) | R | S | I | Informed | Those who are kept up-to-date on progress, typically after a task is completed. Communication with this group is one-way.
| 4 | Business inspection | R | S
| 5 | Performance metric identification | R | S
Design | 1 | Business architecture research | S | R
| 2 | Cloud migration readiness check report | S | R
| 3 | Cloud migration readiness check report review and approval | R | S
| 4 | Network topology solution | S | R
| 5 | LandingZone design(optional) | S | R
| 6 | Business Architecture Design | R | S
| 7 | Migration solution design and review | R | S
| 8 | Migration Plan & WBS | R | S
| 9 | Product Feature Proof of Concept (PoC) Testing & Validation | R | S
| 10 | All products training | S | R
| 11 | DevOps platform adaptation(Tencent can provide Terraform adaptation) | R | S
| 12 | Cloud resources provision | S | R
Implementation | 1 | Cloud foundation/Devops platform deployment | R | S
| 2 | Business platform/Application Infra setup | R | S
| 3 | Migration for each Apps & Platforms | R | S
| 4 | Business scenario testing | R | S
| 5 | Canary release cutover runbook and rollback preparation | R | S
| 6 | Data sync automation & tooling (object storage/image/etc.) | R | S
| 7 | Scale out application workload to the production size | R | S
| 8 | Monitoring platform setup | R | S
| 9 | Canary release drill | R | S
| 10 | Business stress testing | R | S
| 11 | Risk scan (optional) | S | R
Cutover | 1 | Tencent escort support group setup | S | R
| 2 | Canary release running | R | S
| 3 | Application cutover | R | S
Summary & Improvement | 1 | Application stability observation | R | S
| 2 | Application performance optimization | R | S
| 3 | Application HA improvement | R | S
| 4 | Disaster recovery drill | R | S
| 5 | Migration review and summary | S | R
Legend:
R = Responsible
S = Support
- = N/A