## APP Migration SOW
For large-scale, complex migration projects involving numerous applications, it is necessary to compile and organize information on all applications to be migrated and to group them into batches based on their interdependencies.
Stage | Task（Application） | NO. | CSP | Type | App Vendor | Microservices Releated | Functionality | Code refactoring estimation (WIP) | Technical Clarification of Migration SoW | [29 empty] | Planned Start Time | Planned Finish time | Comments
[9 empty] | 01 Assessment |  |  | 02 Design | [5 empty] | 03 Application Modernization & Refactoring |  |  |  | 04 Application Testing & Integration &Verification |  |  |  |  | 05 Implementation | [6 empty] | 06 Cutover |  |  | 07 Handover&Documentation
[9 empty] | Primary Role: 1. Application Architect 2. FinOps Architect 3. Finops Partner |  |  | Primary Role: 1. Terraform Engineer 2. Migration Engineer 3. Application Architect 4. DevOps Engineer 5. FinOps Architect 6. Finops Partner | [5 empty] | Primary Role: 1. Application Developer 2. DevOps Engineer 3. DBA |  |  |  | Primary Role: 1. QA Test Engineer 2. DevOps Engineer 3. DBA |  |  |  |  | Primary Role: 1. Terraform Engineer 2. Migration Engineer 3. DevOps Engineer 4. Developers 5. DBA 6. QA Test Engineer Developers 7. Migration Engineer 8. FinOps Architect 9. Finops Partner | [6 empty] | Primary Role: 1. Migration Engineer 2. Application Architect 3. Developers 4. QA Test Engineer 5. DevOps Engineer 6. DBA |  |  | Primary Role: 1. Tech Writer 2. Migration Enigneer 3. Application Architect 4. QA Test Engineer 5. Devops Engineer 6. DBA
[9 empty] | Activity: 1. Dependency Mapping | 2. Application Assessment | 3. Finops Assessment | Activity: 1. Landing Zone & Application Terraform Construction | 2. Product PoC Verification | 3. Joint LLD Design with Tencent Team for Application | 4. CI/CD Pipeline PoC testing | 5. Observability PoC Testing | 6. FinOps Design | Activity: 1. Application refactoring | 2. CI/CD Integration | 3. Observability Integration | 4. Application Database Schema Conversion | Activity: 1. Functional / Integration Testing | 2. Performance (Load) Testing | 3. CI/CD Verification | 4. Observability Verification | 5. Database verification | Activity: 1. Landingzone/Infrastructure/Application Deployment via Terraform | 2. Infrastructure Migration | 3. CI/CD Deployment | 4. Database deployment | 5. Application Verification | 6. Security Verification | 7. FinOps Deployment | Activity: 1. Cutover Rehearsal | 2. Cutover Execution | 3. Finops Cutover | Activity: 1. Documentation | 2. Knowledge Transfer
Batch 1 | app-xxx | 1 | AWS
| app-yyy | 2 | GCP
| app-zzz | 3 | AWS & GCP
|  | 4 | AWS & GCP
|  | 23 | AWS
Batch 2 | app-xy | 1 | AWS
| api-yy | 2 | GCP
| api-zy | 3 | AWS & GCP
|  | 4 | AWS & GCP
|  | 23 | AWS
Batch N | app-xzz | 1 | AWS
| api-yzz | 2 | GCP
| api- | 3 | AWS & GCP
|  | 4 | AWS & GCP
|  | 23 | AWS

## QA for Apps
# | Question | Answer - APP1 | Answer - APP2 | Answer - APPN
1 | Application owner
2 | What's the microservice migration scope?
3 | What's the programming language?
4 | What's the loadbalancer for application? - external lb (internet-facing) - internal lb
5 | What's the database instances?
6 | Whether database is shared by multiple applications
7 | is there any database specific use cases? - pg: db_link - pg: rds proxy - mysql: rds proxy - documentdb: documentdb driver cases: reuse connection, read/write splitting
8 | What's the s3/GCS storage?
9 | What's the inbound traffic flow? cf->alb->app
10 | What's the outbound traffic flow? - app->nat->internet
11 | What is the current average release cycle for business features?
12 | What's the code development vendor
13 | What is the current code branch manage method?
14 | What's the complete CI/CD pipeline? - gitlab - jenkins - argocd
15 | What's deloyment strategy? Blue-green or Canary deployment?
16 | What's the environment requirement? - sit - staging - prod
17 | Is there a problem of insufficient IP addresses?
18 | Is there any QA testing cases?
19 | How about the automation testing coverage? - by tool - by manual
20 | Who handles the testing - Functional Testing - Integration Testing - UAT Testing
21 | How long it took (e.g, gcp to aws migration) for - Functional Testing - Integration Testing - UAT testing
22 | Does it require performance testing? - if so, how about the performance testing tool and who will cover the performance testing.
23 | Whether it requires penetration testing? - If so, how long it will take based on the previous experience.
24 | What are the application's high availability and disaster recovery mechanisms? For example, cross-AZ and failover mechanisms.
25 | What is the service registration and discovery mechanism? - Spring Cloud Config
26 | How does the application currently retrieve database credentials? Is it via environment variables, local config files, or a secrets manager?
27 | Are there any scheduled/batch job tasks?
28 | what's the internal dependencies?
29 | what's the external dependencies? such as external user and partner usecase.
30 | Does it have a whitelist of IPs, domain name resolution, certificate dependencies, etc.?
31 | Are there any special requirements regarding resource labeling and cost attribution?
32 | whether the application stores any non-ephemeral data (e.g., logs, user uploads, sessions) on the local file system -PVC - S3 - EBS - EFS
33 | What's the endpoints? - public domain - private domain
34 | What's latency requirement?
35 | What's the observability requirement?
36 | What's the logging requirement
37 | what's the aws/gcp sdk dependency
38 | what's the commercial service dependency
39 | who handle the maintenance.
40 | what's the downtime requirement during cutover
41 | Migration strategy